## Sheet1
Issue Description | Talked to Gregg/Jason | JIRA Number | 2.27Update2
In Content Moderation, the semi-newly-added dialogue box includes a misspelling: https://screencast.com/t/sPKIJ80hYhoK (The button should read 'Approve All Content' instead of 'Approval All Content' | YES | https://jira.bbpd.io/browse/SCB-7950 | YES | Passed testing on alpha
Maps & Directions app - attachment works if you create attachment on Add, issue occurs when you create attachment on edit; the links show on EU but don't go anywhere (Don found this was broken when the social media card stuff was done) https://usqaalpha.schoolwires.net/site/default.aspx?PageType=3&ModuleInstanceID=7306&ViewID=503a3e79-9340-40fd-8d85-f3b476c2baf0&RenderLoc=0&FlexDataID=31643&PageID=4035 He says: SaveAttachment FileUpload control save attachment to ...\ModuleInstance\<moduleInstanceId>\Data\<flexrecordid> due to changes for Social Page Options. End user detail view FileLink control expects the image to be located at ...\ModuleInstance\<moduleinstanceId> | YES | https://jira.bbpd.io/browse/SCB-7951 | NO
Calendar - Invalid End Date with 'No End Time' checked skips past event validation | YES | https://jira.bbpd.io/browse/SCB-7953 | YES | Passed testing on alpha
Dashboard - Attendance area - if a field such as 'Period' has no value, it throws the alignment for all of the columns off | YES | https://jira.bbpd.io/browse/SCB-7952 | NO
Dashboard - Site Manager and Notifications icons are not included in the dashboard tour (STORY) | YES | https://jira.bbpd.io/browse/SCB-7955 | NO
New tables can't be added in Classic View with IE 11 only. Happens at least as far back as 2.23. You add app to page, click app, it gives you box to choose amount of rows/columns, but when you've chosen, the table never loads in SM | YES | https://jira.bbpd.io/browse/SCB-7956 | NO
Ally Widget - stays in a state of loading due to automation build problem | YES | https://jira.bbpd.io/browse/SCB-7954 | YES | Passed testing on alpha
Automation - Using the automated builds c2webapp web.config caused errors on initial page | YES | https://jira.bbpd.io/browse/SCB-7947 | NO
Automation - Using the automated builds API v1 web.config caused errors on initial page | YES | https://jira.bbpd.io/browse/SCB-7948 | NO
Dashboard - unpublished photos show in dashboard stream (added as STORY) | YES | https://jira.bbpd.io/browse/SCB-7957 | NO